## Timeline
Task/Milestone | Start Date | Completion Date
Explore application direction (web or application based). | 2017-10-16 | 2017-12-01
Investigate what platform to use for back end. | 2017-10-16 | 2017-12-01
Investigate what framework to use for front end. | 2017-10-16 | 2017-12-01
Implement back end. | 2018-01-08 | 2018-02-12
Test back end. | 2018-02-12 | 2018-02-16
MILESTONE: Functional back end. | X | 2018-02-23
Choose encryption method. | 2018-01-15 | 2018-01-19
Create user authentication. | 2018-01-15 | 2018-01-22
Construct front end. | 2018-01-08 | 2018-02-12
MILESTONE: Functional front end. | X | 2018-02-12
Connect front end to back end. | 2018-02-23 | 2018-03-05
MILESTONE: Front and back end integrated. | X | 2018-03-05
Test combination of front and back end. | 2018-03-05 | 2018-03-09
Refine user experience. | 2018-03-19 | 2018-03-23
MILESTONE: Final testing completed. | X | 2018-03-23
MILESTONE: Final version released. | X | 2018-03-30

## EffortMatrix
Percentage of Effort
Task | Adam | Kevin | Matt | Ryan
Explore application direction (web or application based). | 20% | 20% | 40% | 20%
Investigate what platform to use for back end. | 10% | 70% | 10% | 10%
Investigate what framework to use for front end. | 10% | 10% | 10% | 70%
Implement back end. | 40% | 60% | 0% | 0%
Construct front end. | 0% | 0% | 40% | 60%
Connect front end to back end. | 25% | 25% | 25% | 25%
Test Application | 70% | 10% | 10% | 10%
Choose encryption method. | 40% | 20% | 20% | 20%
Create user authentication. | 20% | 20% | 20% | 40%
Refine user experience. | 10% | 10% | 70% | 10%
| 245% | 245% | 245% | 265% | 1000%